## Sheet1
Sprint | Feature development | Key delieveries | Status
1 | Build a basic website to track the badminton match errors |  | Done
2 | Improve user interaction | 1. Single time request for Match, player name and rally | Done
|  | 2. Interactive court rather dropdown for the area | Done
3. Improve website appeal like a commercial sites, add backgroud images
4. Finetune court size convas to fit in normal phone screen sizes (5inch)
3 | Recorded match data analysis | 1. Group the data into matches, Like when the user selects the certain match, then it should display the data, rather showing all the data in table. It is not usable format now | Planned
|  | 2. Plot the data in a pi-chart format to show how many mistakes were done in which area | Planned
|  | 3. abilitiy to delete the certain match data | Planned
4 | Create a log-in for the users | This will help for users to check the match data they entered. This is also future proof when we commercialize/more people start using | Under review
5 | Create a logo | 1. Change the name to Badminton Match tracker | Done
|  | 2. Create a nice logo | Planned
6 | Test on Mobile during the match | 1. Get the user input on the ease of usage
2. Test if all the button appear optimal size
3. Make sure user do not need scroll a lot as they focus on the match during the live match
5 | Training new programmer | Main programmer (chatGPT) to train new programmer | Done
6 | Video recording | Can you generate the list of errors based on the video, it involves AI | Future
7 | Generate the training guide | Analyse the mistakes and create training guide for the user with consultaiton from good coaches | Future
8 | Generate revenue | Plan for good space for advertizes (Good ads to start with) | Future
|  | Show the sponsors | Future
|  | Connect with Shops to sell their badminton equipment | Future
3 | Add user authentication (Firebase Auth) | Email/password login, link all data to user ID | Planned
3 | User dashboard for personal match history | Show only user’s own matches & error logs | Planned
4 | Mobile-first UI redesign | Canvas and forms optimized for smaller screens | Planned
4 | Responsive court interaction UX | Clickable grid feels natural on phones/tablets | Planned
5 | Basic insights dashboard | Most frequent errors, zones, player trends | Planned
6 | Admin-only features | Delete/edit errors, view all players | Planned
6 | Export to CSV | Download match history and stats | Planned
7 | Abstract database layer | Prepare for migration from Firebase to custom backend | Planned
8 | Migrate to React frontend | Use components, state mgmt, modern dev practices | Planned
9 | Custom domain deployment | Secure custom domain, CI/CD setup | Planned